## Backlog
| User Story | Tasks | Status | Week Completed
1 | As a player I want to be able to use my rod
|  | Implement 'alternating rod' mechanic using a single tap input | Complete | Sprint 2 | 1 - Necessary for game to meet brief (High priority)
|  | Implement collision for player rods | Complete | Sprint 6 | 2 - Needed but not a part of the core game (Mid priority)
|  | Create new input system to allow players to use a power up without using a turn | N/A | - | 3 - "Nice to have" if time allows (Low priority)
|  | Rod sprite | Complete | Sprint 6 (Iterated from previous weeks)
1 | As a player I want to be able to win
1 | As a player I want the game to have a set time
1 | As a player I want to score depending on fish size
|  | Implement a scoring system which adds/deducts points | Complete | Sprint 9 (Iterated from previous weeks)
|  | Display numerical score as an image based tally | Complete | Sprint 7
1 | As a player I want to avoid jellyfish
|  | Jellyfish sprite | Complete | Sprint 3
|  | Implement collision for jellyfish (no user input should be required) | Complete | Sprint 5 (Iterated from previous weeks)
1 | As a player I want to be able to catch fish
|  | Implement collision for small fish | Complete | Sprint 2
|  | Implement collision for medium fish | Complete | Sprint 2
|  | Implement collision for large fish | Complete | Sprint 2
|  | Small fish sprite | Complete | Sprint 3
|  | Medium fish sprite | Complete | Sprint 5 (Iterated from previous weeks)
|  | Large fish sprite | Complete | Sprint 3
1 | As a player I want to see a consistent art style and theme
|  | Art style guide | N/A | -
|  | Background art | Complete | Sprint 7 (Iterated from previous weeks)
|  | Universal button style | Complete | Sprint 4
1 | As a player I want a menu system to navigate the game
|  | Main menu background art | Complete | Sprint 10
|  | Settings | Complete | Sprint 9 (Iterated from previous weeks)
|  | High scores (if implemented) | N/A | -
|  | Implement menu scene in Unity | Complete | Sprint 10
|  | Pause button | Complete | Sprint 5
|  | Pause menu | Complete | Sprint 10
|  | Reset button | Complete | Sprint 5
|  | Instructions screen/pop-up | Complete | Sprint 11 (Iterated from previous weeks)
1 | As a player I want an end game summary so that I can compare my score to my opponents
|  | Concept for end game summary layout | Complete | Sprint 3
|  | Rematch button | Complete | Sprint 5
|  | High score button | Complete | Sprint 5
|  | Exit to menu button | Complete | Sprint 5
|  | Implement win/summary scene in Unity | Complete | Sprint 12
|  | Create scores which carry over from main game | Complete | Sprint 3
|  | Complete artwork for win summary | Complete | Sprint 12 (Iterated from previous weeks)
1 | As a player I want to have a playable character
|  | Concept art | Complete | Sprint 2
|  | Player feedback/survery | Complete | Sprint 2
|  | Final artwork for Otter | Complete | Sprint 4
|  | Implemented mechanics in Unity | Complete | Sprint 2
|  | Turtle sprite | Complete | Sprint 5
1 | As a player I want to have power ups that create dynamic gameplay
|  | Research different types of power ups | Complete | Sprint 2
|  | Concept art for power up buttons | Complete | Sprint 2
|  | Final artwork for power up buttons and their different states | Complete | Sprint 6
|  | Concept art for power up (catchable objects) | Complete | Sprint 5
|  | Final artwork for power up (catchable objects) | Complete | Sprint 12 (Iterated from previous weeks)
|  | Implement collision for jelly power up fish | Complete | Sprint 7 (Iterated from previous weeks)
|  | Implement collision for speed power up fish | Complete | Sprint 7 (Iterated from previous weeks)
|  | Implement mechanics for jelly power up | Complete | Sprint 10 (Bug fixed from previous weeks)
|  | Implement mechanics for speed power up | Complete | Sprint 10 (Bug fixed from previous weeks)
1 | As a player I want to be able to catch up when I'm behind
2 | As a player I want the fish presented to me and my opponent to be balanced and fair
2 | As a player I want to play the game on different devices regardless of resolution |  |  | Sprint 12
2 | As a player I want to have score feedback
2 | As a player I want the final product to be clean and polished | Visual feedback and affordances, bug fixing etc. Ongoing until end of project |  | Sprint 12
|  | See "As a player I want the game to be animated" | - | -
2 | As a player I want to playtest the game
|  | MVP (minimum viable product) | Complete | Sprint 5
2 | As a player I want to have an elegant UI
|  | Research mobile game UI | Complete | Sprint 2
|  | Concept art | Complete | Sprint 2
|  | Timer bar asset | Complete | Sprint 3
|  | Tally art work | Complete | Sprint 3
|  | Create artwork for power-up buttons | Complete | Sprint 6
|  | Animate timer fish | Complete | Sprint 11
2 | As a player I want the game to be animated
|  | Animation system in Unity | Complete | Sprint 10
|  | Animation frames - Small fish | Complete | Sprint 8
|  | Animation frames - Medium fish | Complete | Sprint 8
|  | Animation frames - Large fish | Complete | Sprint 9
|  | Animation frames - Jellyfish | Complete | Sprint 8
|  | Animation frames - Jelly power up fish | Complete | Sprint 12 (Iterated from previous weeks)
|  | Animation frames - Speed power up fish | Complete | Sprint 12 (Iterated from previous weeks)
2 | As a player I want to have audio feedback
|  | SFX - Catch fish | Complete | Sprint 12
|  | SFX - Catch jellyfish (zap) | Complete | Sprint 12
|  | SFX - Catch power up | Complete | Sprint 12
|  | SFX - Catch a gold fish | N/A | Sprint 12
|  | SFX - Activate jelly power up | Complete | Sprint 12
|  | SFX - Activate wave power up | Complete | Sprint 12
|  | SFX - Menu/button press | Complete | Sprint 12
|  | SFX - Rod movement | Complete | Sprint 12
|  | SFX - Round begin | Complete | Sprint 12
|  | SFX - Round mid | Complete | Sprint 12
|  | SFX - Round end | Complete | Sprint 12
|  | OST | Complete | Sprint 12
|  | Implement SFX into Unity | Complete | Sprint 12
|  | Implement OST into Unity | Complete | Sprint 12
3 | As a player I want to have optimised gameplay
3 | As a player I want a high score board so that I compare my scores to that of other players |  | N/A