## Backlog
| User Story | Tasks | Status
1 | As a player I want to be able to use my rod
|  | Implement 'alternating rod' mechanic using a single tap input | Complete |  | 1 - Necessary for game to meet brief (High priority)
|  | Implement collision for player rods | Complete |  | 2 - Needed but not a part of the core game (Mid priority)
|  | Create new input system to allow players to use a power up without using a turn |  | Week 7 | 3 - "Nice to have" if time allows (Low priority)
|  | Rod sprite | Complete
1 | As a player I want to be able to win
1 | As a player I want the game to have a set time
1 | As a player I want to score depending on fish size
|  | Implement a scoring system which adds/deducts points | Complete
|  | Display numerical score as an image based tally |  | Week 7
1 | As a player I want to avoid jellyfish
|  | Jellyfish sprite | Complete
|  | Implement collision for jellyfish (no user input should be required) | Complete
1 | As a player I want to be able to catch fish
|  | Implement collision for small fish | Complete
|  | Implement collision for medium fish | Complete
|  | Implement collision for large fish | Complete
|  | Small fish sprite | Complete
|  | Medium fish sprite | Complete
|  | Large fish sprite | Complete |  | Animation
1 | As a player I want to see a consistent art style and theme |  |  |  | UI tally | Alex T
|  | Art style guide | N/A |  | Turns/power ups (touch boundary) | Alex T
|  | Background art | Complete |  | Assets in scene*
|  | Universal button style | Complete |  | Menu rework
1 | As a player I want a menu system to navigate the game |  |  |  | Spawn refactor
|  | Main menu background art |  | Week 7 | Build deployment
|  | Settings |  | Week 7 | Implement audio
|  | High scores (if implemented) |  | Week 7 | Polish catching fish
|  | Implement menu scene in Unity |  | Week 7
|  | Pause button |  | Week 7
|  | Pause menu |  | Week 7
|  | Reset button |  | Week 7 | * power up fish pick ups
|  | Instructions screen/pop-up |  | Week 7 | * power up button states
1 | As a player I want an end game summary so that I can compare my score to my opponents
|  | Concept for end game summary layout | Complete
|  | Rematch button |  | Week 7
|  | High score button |  | Week 7
|  | Exit to menu button |  | Week 7
|  | Implement win/summary scene in Unity |  | Week 8
|  | Create scores which carry over from main game | Complete
1 | As a player I want to have a playable character
|  | Concept art | Complete
|  | Player feedback/survery | Complete
|  | Final artwork for Otter | Complete
|  | Implemented mechanics in Unity | Complete
|  | Turtle sprite | Complete
1 | As a player I want to have power ups that create dynamic gameplay
|  | Research different types of power ups | Complete
|  | Concept art for power up buttons | Complete
|  | Final artwork for power up buttons and their different states | Complete
|  | Concept art for power up (catchable objects) | Complete
|  | Final artwork for power up (catchable objects) | Complete
Implement collision for jelly power up fish
Implement collision for speed power up fish
Implement mechanics for jelly power up
Implement mechanics for speed power up
1 | As a player I want to be able to catch up when I'm behind
2 | As a player I want the fish presented to me and my opponent to be balanced and fair
2 | As a player I want to play the game on different devices regardless of resolution
2 | As a player I want to have score feedback
2 | As a player I want the final product to be clean and polished
See "As a player I want the game to be animated"
2 | As a player I want to playtest the game
|  | MVP (minimum viable product) | Complete
2 | As a player I want to have an elegant UI
|  | Research mobile game UI | Complete
|  | Concept art | Complete
|  | Timer bar asset | Complete
|  | Tally art work | Complete
Animate timer fish
2 | As a player I want the game to be animated |  |  | Week 9?
Animation system in Unity
Animation frames - Small fish
Animation frames - Medium fish
Animation frames - Large fish
Animation frames - Jellyfish
Animation frames - Jelly power up fish
Animation frames - Speed power up fish
2 | As a player I want to have audio feedback |  |  | Week 8
SFX - Catch fish
SFX - Catch jellyfish (zap)
SFX - Catch power up
SFX - Catch a gold fish
SFX - Activate jelly power up
SFX - Activate wave power up
SFX - Menu/button press
SFX - Rod movement
SFX - Round begin
SFX - Round mid
SFX - Round end
OST
Implement SFX into Unity
Implement OST into Unity
3 | As a player I want to have optimised gameplay
3 | As a player I want a high score board so that I compare my scores to that of other players